## Sheet1
Playbook Name |  | RELEASE MANAGEMENT PLAYBOOK | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call) & Automated Mails
Playbook Type |  | STANDARD OPERATING PROCEDURE | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | Release Manager + Dev Lead + DevOps Manager | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | INITIATION OF A NEW SOFTWARE RELEASE CYCLE | * Weightage allows true depiction of status, each item does not have equal importance
| Milestone | Task | Type | Assignee | Days from Initiation | Weightage
1 | Onset Planning | Jira Ticket: Create a Release Ticket for the upcoming release 14 days ahead of Release. This should be done in Release-Board. Create a Fix version with the Release Ticket Id for eg: RB-73. This fix version will act as a placeholder for the actual fix-version which will be alloted once release is in final phase. | Task | Release Manager |  | 3
2 | Onset Planning | Create a Confluence page containing all the details like release date-time, tickets, Infra changes,rollout plan, rollback plan. Share mail with details / link with all Stakeholders. | Touchpoint | Release Manager |  | 5
3 | Ticket Validation and Collection | Identify the tickets relavent with the current release. Create a fix-version in all of the Jira board where the tickets are with the same name as original Release-Branch ticket. Tag all the tickets with the same fix-version. | Task | Release Manager |  | 3
4 | BRANCHING & DEV | DevTeam should create branches with prefix RB-* from the production, against the Release-Board Ticket. These branches can be used to consolidate all the code from differenct feature branches. | Touchpoint | Release Manager |  | 2
5 | BRANCHING & DEV | Developers fork feature/bugfix branches from the production branch. Ensure ticket ID in the branch name. | Task | Dev Lead |  | 4
6 | BRANCHING & DEV | Developers should get the code reviewed and merge the code to the appropriate branch (RB-*). | Touchpoint | Dev Lead |  | 4
7 | RELEASE PREP | As the release date approaches in 2 weeks, the release manager is responsible for initiating a Freshservice ticket. This ticket should comprehensively detail the impending release, specifying the date-time, and include links to the release's Confluence page that outlines both the Rollout and Rollback strategies. | Touchpoint | Release Manager | 14 | 2
8 | RELEASE PREP | DevTeam to create PR against release-candidate branches. Ensure that all PRs are verified and merged to release-candidate branches, resolving any conflicts in favor of the release-candidate. | Touchpoint | Dev Lead |  | 4
9 | DEPLOYMENT | On the scheduled release date, utilize DevOps or designated teams to prepare for deployment. The DevOps team to perform following checks and balances to kickoff deployment * Ticket Identification: Identify all the ticktes tagged with the placeholder fix-version * Approval Verification: Check that all the PR are approved and merged against release-candidate(minimum 2 reviewers) * Release Version Creation: Create a valid fix-version * Discrepancy Reporting and Resolution: Report any discrepency found out. * Commit ID Verification: Verify each commit is against a valid tagged ticket. This ensure only changes which are sanctioned to go make it to the final build * Updating Tickets with Release Version: Update all the tickets with the valid fix-version, replacing the old placehoder fix-version * Pull Request Creation for Production: Create a PR against the production branch. | Task | DevOps Manager |  | 8
10 | DEPLOYMENT | Trigger the CI/CD pipeline through PR merging. Monitor the deployment through CI/CD tools | Task | DevOps Manager |  | 2
11 | DEPLOYMENT | Once deployment is successful in production, update Jira and other necessary platforms. | Touchpoint | DevOps Manager |  | 2
12 | POST DEPLOYMENT | Post Deployment DevOps team will perform following checks and tasks: * Update JIRA ticket statuses. * Finalize release versions. * Notify the team of the successful deployment. * Tag the repository. * Synchronize release details to centralized storage, e.g., S3 bucket. * QA to publish the combined release notes. | Task | DevOps Manager |  | 4
13 | POST DEPLOYMENT | Ensure that post-deployment, there's a reverse merge to other branches such as staging, QA, dev, and develop branches | Task | DevOps Manager |  | 3