## Slide 1
Free Playbook Template | SOC Compliance
 | Playbook Name |  |  | S0C COMPLIANCE |  | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails, NPS |  |  |  |  | 
 | Playbook Type |  |  | SCHEDULED |  | * Individual Items can be assigned to Any Role within the organization |  |  |  |  | 
 | Playbook Assignee |  |  | COMPLIANCE MANAGER |  | * Individual Timelines are measured in Days from Inception for quick Assessment |  |  |  |  | 
 | Trigger Condition |  |  | One-Time - Based on SOC Finalization date |  | * Critical Tasks are called out to halt proceeding on rest of Playbook, in case this gets delayed |  |  |  |  | 
 |  |  |  |  |  | * Weightage allows true depiction of status, since each item cannot have equal importance |  |  |  |  | 
 |  | Milestone |  | Task |  | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage | 
 | 1 | Pre-Audit |  | Identify the type of SOC audit that needs to be performed for the organization |  | Task | Compliance Manager | 1 | No | 3 | 
 | 2 | Pre-Audit |  | Analyze all the given vendors in the market and organize Demo's about the services provided by them |  | Touchpoint | Compliance Manager | 10 | Yes | 8 | 
 | 3 | Pre-Audit |  | Finalize a vendor that best suits Organization's requirements. |  | Task | Compliance Manager | 15 | Yes | 8 | 
 | 4 | Pre-Audit |  | Identify the audit objectives, scope, and timelines. |  | Task | Compliance Manager | 25 | No | 2 | 
 | 5 | Pre-Audit |  | Assemble a team of internal stakeholders, including IT, security, compliance, and business representatives. |  | Touchpoint | Compliance Manager | 30 | Yes | 2 | 
 | 6 | Pre-Audit |  | Conduct a gap analysis to identify areas of non-compliance and develop a remediation plan. |  | Task | Compliance Manager | 35 | No | 2 | 

## Slide 2
Free Playbook Template | SOC Compliance
 |  | Milestone |  | Task |  | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage | 
 | 7 | Audit |  | Define the controls and procedures that will be assessed during the audit. |  | Task | Compliance Manager | 40 | No | 7 | 
 | 8 | Audit |  | Identify the control objectives, criteria, and documentation required for each control. |  | Task | IT, Dev & HR | 45 | No | 2 | 
 | 9 | Audit |  | Identify the relevant stakeholders for each of the defined controls and assign activities accordingly. |  | Automated Email | Compliance Manager | 50 | No | 5 | 
 | 10 | Review |  | Gather and review relevant documentation, such as policies, procedures, and evidence of control implementation. |  | Task | Compliance Manager | 70 | Yes | 5 | 
 | 11 | Review |  | Ensure documentation aligns with the control objectives and criteria defined in the SOC framework. |  | Task | Compliance Manager | 75 | No | 5 | 
 | 12 | Review |  | Follow-up with the respective stakeholder in case of delays as per agreed timelines. |  | Touchpoint | Compliance Manager | 85 | No | 5 | 
 | 13 | Review |  | Perform testing of controls to validate their effectiveness and adherence to the defined criteria. |  | Task | SOC Vendor | 90 | Yes | 6 | 
 | 14 | Review |  | Use a combination of inquiry, observation, inspection, and re-performance to gather evidence. |  | Task | SOC Vendor | 100 | No | 3 | 
 | 15 | Report |  | Document any control deficiencies or gaps identified during the audit. |  | Task | External Auditors | 110 | No | 5 | 
 | 16 | Report |  | Classify the deficiencies based on severitv and prioritize remediation efforts. |  | Task | External Auditors | 120 | No | 3 | 
 | 17 | Report |  | Develop a remediation plan to address control deficiencies. |  | Task | SOC Vendor | 130 | No | 3 | 
 | 18 | Report |  | Assign responsibilities, set deadlines, and track progress towards remediation. |  | Task | Compliance Manager | 135 | No | 3 | 

## Slide 3
Free Playbook Template | SOC Compliance
Being SOC Compliant is important for success and growth of your customers and business.
SOC compliance is crucial for protecting sensitive data, managing risks, meeting legal requirements, building trust with stakeholders, and gaining a competitive advantage in the market.
An effective SOC compliance process involves scoping, risk assessment, control identification and documentation, control implementation, control testing, remediation, monitoring and continuous improvement, and reporting.
We hope you found this template useful!
At SmartKarrot, we automate the SOC Compliance process using SmartPlaybooks. Ensure proper tracking, reduce effort and cost with SmartKarrot.
To see how it works, reach out to playbooks@smartkarrot.com
 |  | Milestone |  | Task |  | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage | 
 | 19 | Approval |  | Review the audit report with key stakeholders, including management and compliance teams. |  | Task | Executive Sponsor | 145 | Yes | 8 | 
 | 20 | Approval |  | Obtain necessary approvals and sign-offs on the audit findings and recommendations. |  | Touchpoint | Executive Sponsor | 150 | Yes | 6 | 
 | 21 | Approval |  | Establish processes for ongoing monitoring, evaluation, and improvement of controls. |  | Task | Compliance Manager | 155 | No | 3 | 
 | 22 | Approval |  | Regularly review and update documentation to reflect changes in systems, processes, and regulations. |  | Task | Compliance Manager | 155 | No | 3 |