## Sheet1
Playbook Name |  | S0C COMPLIANCE | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails, NPS
Playbook Type |  | SCHEDULED | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | COMPLIANCE MANAGER | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | One-Time - Based on SOC Finalization date | * Critical Tasks are called out to halt proceeding on rest of Playbook, in case this gets delayed
* Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage
1 | Pre-Audit | Identify the type of SOC audit that needs to be performed for the organization | Task | Compliance Manager | 1 | No | 3
2 | Pre-Audit | Analyze all the given vendors in the market and organize Demo's about the services provided by them | Touchpoint | Compliance Manager | 10 | Yes | 8
3 | Pre-Audit | Finalize a vendor that best suits Organization's requirements. | Task | Compliance Manager | 15 | Yes | 8
4 | Pre-Audit | Identify the audit objectives, scope, and timelines. | Task | Compliance Manager | 25 | No | 2
5 | Pre-Audit | Assemble a team of internal stakeholders, including IT, security, compliance, and business representatives. | Touchpoint | Compliance Manager | 30 | Yes | 2
6 | Pre-Audit | Conduct a gap analysis to identify areas of non-compliance and develop a remediation plan. | Task | Compliance Manager | 35 | No | 2
7 | Audit | Define the controls and procedures that will be assessed during the audit. | Task | Compliance Manager | 40 | No | 7
8 | Audit | Identify the control objectives, criteria, and documentation required for each control. | Task | IT, Dev & HR | 45 | No | 2
9 | Audit | Identify the relevant stakeholders for each of the defined controls and assign activities accordingly. | Automated Email | Compliance Manager | 50 | No | 5
10 | Review | Gather and review relevant documentation, such as policies, procedures, and evidence of control implementation. | Task | Compliance Manager | 70 | Yes | 5
11 | Review | Ensure documentation aligns with the control objectives and criteria defined in the SOC framework. | Task | Compliance Manager | 75 | No | 5
12 | Review | Follow-up with the respective stakeholder in case of delays as per agreed timelines. | Touchpoint | Compliance Manager | 85 | No | 5
13 | Review | Perform testing of controls to validate their effectiveness and adherence to the defined criteria. | Task | SOC Vendor | 90 | Yes | 6
14 | Review | Use a combination of inquiry, observation, inspection, and re-performance to gather evidence. | Task | SOC Vendor | 100 | No | 3
15 | Report | Document any control deficiencies or gaps identified during the audit. | Task | External Auditors | 110 | No | 5
16 | Report | Classify the deficiencies based on severitv and prioritize remediation efforts. | Task | External Auditors | 120 | No | 3
17 | Report | Develop a remediation plan to address control deficiencies. | Task | SOC Vendor | 130 | No | 3
18 | Report | Assign responsibilities, set deadlines, and track progress towards remediation. | Task | Compliance Manager | 135 | No | 3
19 | Approval | Review the audit report with key stakeholders, including management and compliance teams. | Task | Executive Sponsor | 145 | Yes | 8
20 | Approval | Obtain necessary approvals and sign-offs on the audit findings and recommendations. | Touchpoint | Executive Sponsor | 150 | Yes | 6
21 | Approval | Establish processes for ongoing monitoring, evaluation, and improvement of controls. | Task | Compliance Manager | 155 | No | 3
22 | Approval | Regularly review and update documentation to reflect changes in systems, processes, and regulations. | Task | Compliance Manager | 155 | No | 3