## Sheet1
Playbook Name |  | MONTHLY SOFTWARE DELIVERY REVIEW | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails
Playbook Type |  | SCHEDULED - 2nd Tuesday of EVERY MONTH (for Previous Month) | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | ACCOUNT MANAGER / CUSTOMER SUCCESS MANAGER | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | PRESET [DATE + FREQUENCY] | * Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Weightage
1 | FINANCE | Review Delivery + Infra Expenses for Previous 2 months. Forecast Budget and Expenses for the next two quarters, and for the financial year.Look at adherence to the forecast in the last 2 quarters. Discuss causes of variance and create action items and owners, if any are required. | Task | Delivery Manager | 1 | 3
2 | FINANCE | Review Revenue Managed and Margin analysis for the current quarter. Compare the numbers against plan. Discuss causes of variance and create action items and owners, if any are required. | Task | Delivery Manager | 1 | 4
3 | DEVELOPMENT | Review Important Plans like Development Plan, Sprint Plan, Testing Plan, Automation Plan, Deployment Plan, etc. as relevant and make sure they are updated based on the latest events and changes. | Task | Program Manager | 1 | 5
4 | DEVELOPMENT | Review ALL Important Delivery Metrics - Business Value Delivered, Deployment Frequency, Team Velocity, etc. and check if they are within acceptable / planned ranges. Discuss causes of variance and create action items and owners, if any are required. | Task | Project Manager | 1 | 8
5 | DEVELOPMENT | Review other Processes / Plans like DevOps, Build Process, Deployment Process to validate if they are well documented, and appropriately followed. Ensure that team is aptly aware how to handle them. | Task | Project Manager | 1 | 5
6 | DEVELOPMENT | Review Infrastructure avaialble to team - Cloud, Laptops, Network, Video Conf Equipment, Licenses, anything else that might be required specifically for this Account. Discuss challenges (if any) and create action items and owners, if required. | Task | Quality Manager | 1 | 3
7 | QUALITY | Review ALL Important Quality Metrics - Escaped Defects Rate, Defect Density, Code Coverage, Testing Automation %, Performance Automation etc. Discuss causes of variance and create action items and owners, if any are required. | Task | Quality Manager | 1 | 5
8 | QUALITY | Review Unit Testing Plan and Execution. Review Security Aspects in great detail.Discuss causes of concern (if any) and create action items and owners, if required. | Task | Quality Manager | 1 | 5
9 | RELATIONSHIP | Review Relationship Heat Map with Client Stakeholders. Discuss Champions, potential loss of any, how to add more to the group. Discuss detractors and ideas on how to turn things around, as appropriate. | Task | Account Manager / Customer Success Manager | 1 | 6
10 | RELATIONSHIP | Review last CSAT Survey / NPS and score and create / review Action Items. Discuss next CSAT Survey / NPS, who would run it and when, and what all should be covered in the new survey. | Task | Account Manager / Customer Success Manager | 1 | 8
11 | TEAM | Review Team Satisfaction Levels, attrition nos, weariness levels, overall sentiment. Discuss Action items from the past and new ones that need to be added. | Task | Project Manager | 1 | 5
12 | TEAM | Review New Positions open, or ones that need to be opened. Discuss hiring strategy, challenges in the past, How to maintain and Improve Talent Density etc. | Task | Delivery Manager | 1 | 6
13 | TEAM | Review Team Development, L&D Plan, and Individual Growth Plans. Review Performance Management Results for last cycle and what to do for overall better scores in the next cycle. | Task | Project Manager | 1 | 8
14 | PROGRAM | Executive Reporting. Encapsulate the Review in a high level view with appropriate information, data and dashboards to share with Executive Leadership. Follow up with a call / meeting, if required. | Touchpoint | Program Manager | 1 | 5