## Product Release Management
Playbook Name |  | PRODUCT FEATURE RELEASE | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails
Playbook Type |  | MANUAL - WHEN NEW SPRINT PLAN IS FINALIZED | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | PRODUCT MANAGER, PRODUCT HEAD | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | MANUAL | * Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Weightage
1 | Planning | Collect and document user stories & requirement | Task | Product manager | 1 | 1
2 | Planning | Develop screens/wireframes | Task | Product manager | 5 | 2
3 | Planning | Handover approved wireframes to engineering team and get a sign off | Task | Product manager | 10 | 8
4 | Planning | Create dev plan and share with management | Task | Engineering team | 13 | 3
5 | Development | Confirm product development completion - sprint cycle | Task | Engineering team | 15 | 3
6 | Development | Engineering team to Handover to QA team for testing | Task | Engineering team | 25 | 5
7 | Development | QA team to confirm - Testing completed | Task | Quality Assurance | 30 | 10
8 | Development | QA team to Handover for release back to Engineering team | Task | Quality Assurance | 33 | 6
9 | Development | PM team to Demo to management | Task | Product manager | 35 | 4
10 | Release | Management approval based on the demo | Task | Product manager | 38 | 8
11 | Release | Pushed for release | Task | Engineering team | 40 | 5
12 | Release | Release completed & release notes circulated | Task | Product manager | 45 | 8
Feature release