## IT Sourcing - Client onboardOng
Playbook Name |  | IT Sourcing Client Onboarding | * Playbook Items consist of Tasks, Meetings, Automated Mails, Videos, etc.
Playbook Type |  | MANUALLY SETUP | * Individual Items can be assigned to Any Role/User within the organization
Playbook Assignee |  | Delivery head and Client Partner | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | Contract stage: To be Signed | * Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Weightage
1 | Pre-Boarding | Contract Finalization: Finalize and sign the outsourcing agreement, setting clear expectations on scope, deliverables, timelines, and SLAs. | Task | Contract Manager | 5 | 10
2 | Pre-Boarding | Kick-off Meeting: Conduct a meeting to establish project goals, timelines, roles, and communication strategies with key stakeholders. | Task | Project Manager | 7 | 9
3 | Pre-Boarding | IT Infrastructure Assessment: Evaluate the client's current IT setup to identify improvement areas and assess compatibility with our infrastructure. | Task | IT Analyst | 10 | 8
4 | Pre-Boarding | TOM Definition : Develop a collaborative roadmap for the future state of IT operations, including process, technology, and governance. | Task | Strategy Consultant | 15 | 9
5 | Pre-Boarding | Transition Planning: Create a detailed plan covering all migration aspects like data transfer and security, ensuring a smooth transition. | Task | Project Manager | 20 | 10
6 | Service Initiation | Infrastructure Setup: Set up necessary IT infrastructure like servers, network devices, and software required for service delivery. | Task | IT Specialist | 25 | 8
7 | Service Initiation | Security Measures Implementation: Implement security protocols to protect client data in compliance with regulations and establish cybersecurity measures. | Task | Security Officer | 30 | 9
8 | Service Initiation | Data Migration: Transfer client data and applications to our systems while ensuring integrity and confidentiality during the process. | Task | Data Manager | 35 | 10
9 | Service Initiation | Service Launch: Launch the initial IT services as per the contract, ensuring all systems are operational and integrated. | Task | Operations Manager | 40 | 8
10 | Service Initiation | User Training: Provide comprehensive training on new systems and processes, and set up support for any arising user issues. | Task | Training Coordinator | 45 | 7
11 | Stabilization | Performance Monitoring: Monitor service delivery against KPIs and SLAs, reporting findings to stakeholders and making adjustments as needed. | Task | Quality Analyst | 50 | 9
12 | Stabilization | Process Improvement: Identify and implement improvements to IT processes and services to enhance quality and efficiency continuously. | Task | Process Manager | 55 | 8
13 | Stabilization | Change Management: Manage and implement necessary changes in IT services or infrastructure in response to client's evolving needs. | Task | Change Manager | 60 | 7
14 | Stabilization | Issue Resolution: Address any service issues promptly, collaborate with the client for solutions, and adjust processes for improvement. | Task | Support Manager | 65 | 10
15 | Ongoing Support | Account Management: Assign a dedicated account manager to be the primary contact, analyzing all communications and managing the client relationship. | Task | Account Manager | 70 | 8
16 | Ongoing Support | Regular Reviews: Conduct regular strategy reviews with the client to assess service performance and align on future objectives. | Task | Strategy Consultant | 75 | 7
17 | Ongoing Support | Innovation Exploration: Identify opportunities to apply our IT expertise to innovate and support the client's strategic business goals. | Task | Innovation Manager | 80 | 6
18 | Ongoing Support | Relationship Building: Strengthen the client relationship through regular communication, trust-building, and collaborative initiatives. | Task | Relationship Manager | 85 | 9
Performance Monitoring
Performance Monitoring
Performance Monitoring