## Cross-sell
Playbook Name |  | ACCOUNT CROSS-SELL | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails, NPS
Playbook Type |  | AUTOMATED / SCHEDULED | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | CUSTOMER SUCCESS MANAGER | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | ACCOUNT SEGMENT/CROSS-SELL TRIGGER | * Critical Tasks are called out to halt proceeding on rest of Playbook, in case this gets delayed
* Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage
1 | QUALIFICATION | Identification: Review the list of accounts. Assess the health score, utilization, touchpoints, account notes through customer list view and account 360 view. Review product console for each account | Task | Customer Success Manager | 1 | No | 1
2 | QUALIFICATION | Schedule Discovery: Identify relevant stakeholder/s by account. Update the account plan with added value through the cross-sell. Schedule connect with customer stakeholder/s. | Task | Customer Success Manager | 1 | No | 2
3 | QUALIFICATION | Internal Discussion: Discuss the accounts to ensure that the internal team are prepared at their end | Task | Customer Success Manager Account Manager | 2 | No | 3
4 | DISCOVERY | Prep: Create a cross-sell asset addressing value add-ons to the customer. Identify gaps/questions that the customer needs to be asked | Task | Account Manager | 3 | No | 2
5 | DISCOVERY | Discovery Session: Connect with stakeholder/s (1-1 or group) for feedback and to validate pain points and/or other desired outcomes | Touchpoint | Customer Success Manager Account Manager | 8 | Yes | 5
6 | DISCOVERY | Follow up Email - Basis discovery, create a brief Cross-sell Plan (bullet points could do). Share the plan with all relevant stakeholder, and also add to "Account Notes' | Touchpoint | Account Manager | 8 | No | 2
7 | PRESENTATION | Review Discovery Call: Quantify the pain points / outcomes through appropriate metrics. Identify and record the value proposition of the proposed product (complementary, additional efficiency, higher ROI) | Task | Account Manager | 10 | No | 4
8 | PRESENTATION | Schedule connect with stakeholders (1-1 or group) to review the value proposition | Touchpoint | Account Manager | 10 | No | 2
9 | PRESENTATION | Finalize Cross-sell asset: Review the asset and proposed value with CSL for any inputs and modify, as required. | Task | Customer Success Manager Customer Success Leader | 13 | No | 3
10 | PRESENTATION | Communicate the Cross-sell Proposal: Present the proposed value to the customer addressing their desired outcomes and get their buy-in. | Touchpoint | Customer Success Manager Account Manager | 17 | Yes | 8
11 | PRESENTATION | Follow up Email - Send a summary of discussion to the customer and internal stakeholder/s. | Touchpoint | Account Manager | 17 | No | 5
12 | CONTRACT | Proposal Creation - Create a formal Cross-sell contract based on discussions. | Task | Account Manager | 23 | No | 5
13 | CONTRACT | Communicate the Cross-sell Process: Clearly communicate the cross-sell process, timeline, add-on pricing and terms to the customer through an email. | Touchpoint | Account Manager | 24 | No | 4
14 | CONTRACT | Follow up Meeting (If required) - Final Contract Negotiations and Discussions. Keep Finance Manager informed of all details on what / when / how to proceed on the next step. | Touchpoint | Finance Manager | 31 | No | 3
15 | CONTRACT | Send mail / details that will allow client to process payment. Ensure plans for the following year are communicated and payment is received. | Touchpoint | Finance Manager | 33 | Yes | 6
16 | CLOSURE | Review and Share Details: Ensure that the cross-sell details are shared with internal stakeholder/s to assist in successful customer onboarding and added to "Account Notes'. | Task | Customer Success Manager | 35 | No | 3
17 | CLOSURE | Celebrate Success: Recognize and celebrate the successful cross-sell with your team to foster positive relationships and recognize great work at an appropriate juncture. | Task | Account Manager | 40 | No | 3